## Efforts
|  |  | Total PDs | 10 | 22 | 165 | 190 | 112 | 499
|  |  | Total PDs for Frontend | 3 | 14 | 105 | 35 | 40 | 197
|  |  | Total PD'S for backend | 7 | 8 | 60 | 155 | 72 | 302
|  |  | Scale in PDs | 1 | 2 | 3 | 5 | 8 |  | UI Estimates
|  |  | Complexity Count for Frontend | 3 | 7 | 35 | 7 | 5 | 57
|  | Total | Complexity Count for Backend | 7 | 4 | 20 | 31 | 9 | 71
Sr. | Module/Screen/Feature | Sub Module / Additional Options | Description | Complexity | [5 empty] | Complexity
| Module/Screen/Feature | Additional Options | Details | Very Simple | Simple | Medium | Complex | Very Complex |  | Very Simple | Simple | Medium | Complex | Very Complex
| Login Screen | Login Screen | Authentication with User Name & Password Authorization details to read from OnePlace i.e. Integration |  |  |  | 1 | [6 empty] | 1
| Market Security (Client Site Home Page) | Link to Market Security - Client Home Page | Opens in a new tab | 1 | [5 empty] | 1
| Market Security - Client Home Page | Export to excel, Contact Market Security |  |  |  | 1 | [5 empty] | 1
| What's New | List of Carriers with fields - Date, Willis Code, Name, Country, Category, Current, Previous Link for each Carrier navigates to Carrier Documents screen | List of Carrier for which changes has been done |  |  | 1 | [5 empty] | 1
| Client Selection | Generic Page to allow selection of Clients | Dropdown with list of Clients |  |  | 1 | [5 empty] | 1
| Carrier Search | Button options - Find and Reset Link - Refresh Data |  |  |  |  | 1 |  |  |  |  | 1
| Basic | Client Name display |  |  |  |  | 1 |  |  |  |  | 1
|  | Select Clients button | Used to select a Client
Legal Name input and criteria (Beginning & Containing)
Country dropdown
Category dropdown
Code input and criteria (Willis, LORS, NAIC, FEIN/AIIN, Client Ref)
State dropdown
Favorites dropdown
| Advanced | Ownership dropdown |  |  |  |  | 1 | [5 empty] | 1
Company Type dropdown
License Country dropdown
Location dropdown
Type dropdown
Rating Agency dropdown
Rating Range dropdown
|  | Approval Status dropdown | Displayed only for Admin user | [9 empty] | 1
|  | Business Unit dropdown | Displayed only for Admin user
|  | Qualifier dropdown | Displayed only for Admin user
|  | Operating Category dropdown | Displayed only for Admin user
|  | Restriction dropdown | Displayed only for Admin user
|  | TOBA dropdown | Displayed only for Admin user
|  | Legal Entity dropdown | Displayed only for Admin user
|  | Advanced (CheckBox) | Displayed only for Admin user
| Default Carriers | Legal Name, Match Type, Country, State, Company Type, Willis Code, LORS Code, NAIC Code, FEIN/AIIN Code, A.M.Best, SAP, Moody's, Fitch, As at date, PHS/SHF/Capacity, NWP, Combined Ratio %, Approval Status, Sanction Status, Toba End Date, Toba Indicator, Fatca Status. Above Highlighted fields are visible only to Admin user | All Carriers - Checkbox to check all carriers Sorting option for each column in the list |  |  | 1 | [7 empty] | 1
| Carrier Favorite options | This is button option | This button option will redirect to Cariier Favorite screen | 1 | [5 empty] | 1
| Favourite Mode Selection | Popup to select mode - Client or Personal (radio button) | This popup comes in case of Admin user |  | 1 | [6 empty] | 1
| Carrier Favorite Screen | Category - New | Button option to create |  |  |  |  | 1 | [5 empty] | 1
|  | Category - Dropdown | Category dropdown
|  | Category - Edit | Button option to edit
|  | Category - Delete | Button option to delete
|  | Carrier Favorite - New | Button option to create
|  | Carrier Favorite - Dropdown | Carrier dropdown
|  | Carrier Favorite - Edit | Button option to edit
|  | Carrier Favorite - Delete | Button option to delete
|  | Carrier Favorite - Add to Category (Copy Category) | This is to Copy Category
|  | Add Carriers | Link to Add Carriers - Navigates to Search Carrier screen
|  | Remove | Link to Remove Carrier from the grid
|  | List of selected Carriers with column sorting option | Legal Name, Country, State, Willis Code
| Email notification options | This is button option | This button option will redirect to Client Notification Screen | 1 | [5 empty] | 1
| Client Notification Screen | Carrier Rating Change Notification Checkbox | Checkbox |  |  |  | 1 | [5 empty] | 1
|  | Selected Carriers list | List
|  | What's New Notification Checkbox | Checkbox
|  | Frequency - Daily, Weekly | Radio Buttons
|  | Category dropdown | Dropdown
|  | Choose Category button | Button
|  | Favorites dropdown | Dropdown
|  | Choose Favorites button | Button
|  | Carrier Search button | Button
|  | Remove Selected button | Button
|  | Save button | Button
|  | Cancel button | Button
| Notification Jobs/Service |  | New Batch job service to read notification profile and send notifications |  |  |  | 1
| Report functions | Reports Page | Client Reports Screen | 1 | [6 empty] | 1
| Ratings Report | Date Range options - Start Date & End Date | XLS and PDF report option having columns - Carrier, Country, Willis Code, Ownership, Compnay Type, Client Reference, FEIN/AIIN, Date Of Action, Type Of Action, New Rating, Old Rating, New Outlook, Old Outlook |  |  | 1 | [5 empty] | 1
| Financial Report | Options - Full Year(s) - Last 5 years Last Quarter - Only for US Carriers | Only XLS report option having columns - Carrier Name, Country, Willis Code, Ownership, Company Type, Client Reference, FEIN/AIIN Code, Year, Liquid, investments, Interest in affiliates, Market value adjustment, Life insurance assets, Total Assets, Gross outstanding claims provision, Net outstanding claims provision, Net technical provisions, Borrowings, Adjusted shareholders' funds, Gross written premium, Net written premium, Net earned premium, Net losses incurred, Underwriting result, Investment result, Operating result, Pre-tax result, Combined ratio, Source |  |  |  |  | 1 |  |  |  | 1
| License Report | Date Range options - Start Date & End Date | This is only XLS report and for only one location (Carrier), columns - Carrier, Country, Willis Code, Ownership, Company Type, Client Reference, FEIN/AIIN, License Type, Description, License Country, License Status |  |  | 1 |  |  |  |  | 1
| Ratings Movement Report | Date Range options - Start Date & End Date | XLS and PDF report option for each rating agency (AMBest, S&P, Moody's, Fitch). Each rating agency will have different list of columns. |  |  | 1 |  |  |  |  | 1
| Print Details | PDF file gets generated for selected carriers | PDF report with sections - Location, Market Ratings, Rating Summary, Capacity, Balance Sheet, Income Statement, Key Ratios, Disclaimer The above details will be repeated for each selected carrier in the same PDF file. |  |  |  | 1 |  |  |  |  | 1
| Excel Download | Excel file gets generated for selected carriers | For selected carriers - Excel will have report similar to information displayed on screen and additional sub-columns for each rating agency. Also for Admin user, Approval Status columns will be displayed. |  |  | 1 | [5 empty] | 1
| PDF Download | PDF file gets generated for selected carriers | For selected carriers - PDF will have report similar to information displayed on screen. Also for Admin user, it will ask whether report is for client? If Yes then it does not show Approval Status column otherwise it will display it. |  |  | 1 | [5 empty] | 1
| Approval Status Download | Displayed only for Admin user | Offline file and email |  |  | 1 |  |  |  |  | 1
| Factsheet Download |  | Offline file and email |  |  |  |  | 1
| TOBA Status | Displayed only for Admin user Excel file gets generated for selected carriers | Excel file gets generated for selected carriers with columns - Legal Name, Country, State, Willis Code, LORS Code, TOBA, Legal Entity, TOBA Type, TOBA Clause TPR, TOBA Clause TRS, TOBA Clause TRF, TOBA Clause TRT, TOBA Clause TBP, TOBA Clause TBR, TOBA Clause TBC, TOBA Clause TRP, TOBA Clause TRR, TOBA Clause TRC, TOBA Clause INT, TOBA Clause PAP, TOBA Clause MIA |  |  |  | 1 |  |  |  |  | 1
| FATCA Compliance | Excel file gets generated for selected carriers | Excel file gets generated for selected carriers with columns - Name, Country, State, Company Type, Willis Code, LORS Code, NAIC Code, FEIN/AIIN Code, FATCA Compliance, FATCA Certificate Type, FATCA Certificate Number, FATCA Entity Type, FATCA Start Date, FATCA Expiry Date |  |  |  | 1 |  |  |  |  | 1
Carrier Detail
| General | Buttons options - Export to PDF Willis short names | Contact Details - Country, State, Type, Group, Main Entity, FATCA Compliance Status, FATCA Certificate Number, FATCA Entity Type, Willis, FEIN, NAIC, LORS, FET Ind, TOBA, TOBA Type, Established Date, Operating category, Comments, Organization Type, MArket Security Contact, Market Security Analyst Approval Status - Internation Status, Qualifiers Comments, Approval Status Changes Popup Ratings Summary (AMBest, S&P, Moody's, Fitch)- Current Rating Agency, Ratings, Outlook, Date, Reference, History, Rating Summary History Popup (4 popups) Documents - Fact Sheets, Rating Rationale, FATCA Certificate, Other |  |  |  | 1 |  |  |  |  | 1
| Summary (default view) | Button options - Client Reference Save, Email notification, Export to Excel, 1 page PDF & Full PDF | Sections - Client Reference, Company details & link to website, Current Rating Agency, Key Financial & Ratios, 5 year rating history for A.M.Best and S&P with tow graphs. Popups to show summary against each graph |  |  |  |  | 1 |  |  |  | 1
Financials
| Balance Sheet - Assets | Button options - Export to Excel, 1 page PDF & Full PDF | Sections - Tabular balace sheet details and Pie chart graph |  |  |  | 1 | [5 empty] | 1
| Balance Sheet - Liabilities | Button options - Export to Excel, 1 page PDF & Full PDF | Sections - Tabular balace sheet for liabilities details and Bar chart graph |  |  |  | 1 |  |  |  |  | 1
| Income Statement | Button options - Export to Excel, 1 page PDF & Full PDF | Sections - Tabular Income Statement details and Bar chart graph |  |  |  | 1 |  |  |  |  | 1
| Ratios | Button options - Export to Excel, 1 page PDF & Full PDF | Sections - Tabular Ratios information - Key, Profitability, Portfolio, Leverage, %, Net, IRIS; and Solvency Ratio (Bar chart) |  |  |  | 1 |  |  |  |  | 1
| Carrier Documents | Export to PDF | Sections - Fact Sheets - (multiple doc selection with links), Rating Rationale - (multiple doc selection with links) and FATCA Certificate - (multiple doc selection with links) |  |  | 1 | [5 empty] | 1
| Licenses | Button options - Export to Excel and PDF | Default view - Each State as a link with common popup having Country of domicile and Link to licensing authority website |  |  |  | 1 |  |  |  |  | 1
| Rating Change Notification | Covered in - Client Notification Screen
| Client Documents | Button option - Export to PDF No data to verify | Sections - Client documents, My documents and Batch print documents |  |  |  |  | 1 |  |  |  | 1
| Help Guide | Link to Help PDF file | Opens in a new tab | 1 | [6 empty] | 1
| Library | Link to other URL | Opens in a new tab and shows the SharePoint document library for Market Security Group | 1 | [6 empty] | 1
| Related Links | Link to other URL | Opens in a new tab and shows the SharePoint Home Page for Market Security Group | 1
| Document Search | Access Denied |  |  |  | 1 | [5 empty] | 1
| Recently viewed carriers |  | Display list having 10 recently viewed Carriers. Recently viewed Carrier will be listed first in the sequence. Each will have link to Carrier Details screen (General Info) and opens in the same screen. |  |  | 1 | [6 empty] | 1
Market Security Admin - menu
| Add/Edit User | Search User |  |  |  | 1 | [6 empty] | 1
Save User Role
|  | Fetch Client List | Gets the client details in the drop down
| Client Maintanence | [6 empty] | 1 | [5 empty] | 1
| Edit Client | Fetch Client List
Fetch Carrier List
Import Carrier List
Import associated categories
Add associated categories
Remove associated categories
Add associated favourites
Import associated favourites
Remove associated favourites
Save
Create Client
|  | Select client pop up | Pop up fetches the country information and retrieves client list
Import carriers
|  | Carrier Search | To add new carriers
Add associated categories
Import associated categories
Remove associated categories
Add associated favourites
Import associated favourites
Remove associated favourites
Save Client
| Home Page Admin | Save | Save home page data |  | 1 | [6 empty] | 1
Reports
Set Reports
|  | Audit Trail Reports | Audit reports for around 50 criteria. Filter Criteria- Select an audit change eg.Carrier- Approval Status, Carrier- Fitch Rating Date Period Report Columns- Unique Code Country Legal Name Date of Change Significant Item Changed New Previous Reason for Change |  |  |  | 1 |  |  |  |  | 1
|  | Approved List |  |  |  |  | 1 |  |  |  |  | 1
|  | Carrier Approval Status Reports | Filter Criteria - Report Type (By Approval Status etc) Value Report Columns - Unique Code Legal Name Approval Status State Country |  |  |  | 1 |  |  |  |  | 1
|  | Operating Status/Company Type Report | Filter Criteria - Report Type (Operating Status, Company Type) Operating Status Report Columns - Country State Legal Name Unique Code/NAIC Operating Status |  |  |  | 1 |  |  |  |  | 1
|  | Group Report | unable to open the report |  |  |  | 1 |  |  |  |  | 1
|  | Rating Update Report | Filter Crieria - Rating Agency Date Period Report column- Country State Legal Name Company Type New Value Best Financial Size Old Value Date Of Change |  |  |  | 1 |  |  |  |  | 1
|  | Marketing Report - Comparative Ratings | Filter Criteria - From Date To Date Report Details - Year wise comparison of carrier ratings |  |  |  | 1 |  |  |  |  | 1
Customized Reports (MSD Only)
|  | Customized Reports (MSD Only) | Filter Criteria - Administration Category Report Columns Code Description |  |  |  | 1 |  |  |  |  | 1
|  | Administration Code Report | Filter Criteria - Approval Type Report Columns - Name Value |  |  |  | 1 |  |  |  |  | 1
|  | Market Comparison Report | Filter Criteria - Year,company type, country,upper limit, sort by Report Fields- Carrier Country Shareholder's funds in 000's Total assets in 000's Gross Premium in 000's Net Premium in 000's Underwriting result Pre-tax result Solvency Ratio Current Rating |  |  |  | 1 |  |  |  |  | 1
|  | Rating Agency Code Report | Filter Criteria- Report Type Report Columns- Rating Agency Website |  |  |  | 1 |  |  |  |  | 1
| Announcements | [5 empty] | 1 | [5 empty] | 1
Fetch Document List
Fetch External Link
Fetch Available Client List
Save
Email Announcement
| Rating Scale |  | Static display of rating scale |  | 1 | [5 empty] | 1
| Document Folder | Fetch Folder List |  |  |  |  | 1 | [6 empty] | 1
Fetch Group List
|  | Add Folder | Interaction with Sharepoint service
| Document Access | [6 empty] | 1
By Documents
Fetch Document List
Fetch Client List
Fetch User List
Add Client
Add User
By Client
Fetch Document List
Fetch Client List
Add Document
By User
Fetch User List
Fetch Document List
Add Document
| Manage Disclaimers | [10 empty] | 1
|  | Save Disclaimers |  |  | 1
| Mosaic DB - Data Migration | [6 empty] | 1
| Signet Data Replication | [6 empty] | 1
| Mosaic Document Migration | [5 empty] | 1
| Willis Permissions Data Replication |  |  |  |  | 1
| Dynamic content or change layout to Client or Willi users | User can change the theme e.g. Font, font color, header color etc |  |  |  | 1
| Update Logo and Disclaimer in Exported Docs |  |  |  |  | 1
| Client Access Report | [5 empty] | 1
| Client Usage Statistics | [5 empty] | 1
| Restriction on Number of carriers for a client |  |  |  |  | 1
| Remove client access | Manual access removal for Admin |  |  |  | 1
| Terms & Conditions Acceptance for new users |  |  |  |  | 1
|  | Total |  | 7 | 4 | 20 | 31 | 9 |  | 3 | 7 | 35 | 7 | 5
|  | Grand Total - Modules/Screens/Features |  | 71 | [5 empty] | 57

## Plan-1 (hidden)
# | Activities | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1 | Knowledge Transfer
2 | Design Document + Sign Off
2 | Solution Setup
3 | Current Risk Level Report
4 | Targeted Email Alerts
5 | SIC Code for Clients
6 | New Client with all Features
7 | Hide Admin Pane by default
8 | Hide the K&R section
9 | Sectionwise Country Report
10 | Country Report with Travel Guidance
11 | New Layer -Live Wind
12 | Travel Guidance Report
13 | Security Risk Updates Report
14 | Political Risk Updates Report
15 | Admin Enhancements
16 | Test Case Preparation
17 | QA
18 | QA Support
19 | Release to IAT
20 | Security Testing
21 | IAT Testing
22 | Performance Testing
23 | Release to Prod
24 | Warranty & Support
Resources
Sr. Developer
Jr. Developer
QA

## Cost-1 (hidden)
Role | Locaton | Daily Rate | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Sr. Developer | India | 224 | Week 0: 5; Week 1: 5; Week 2: 5; Week 3: 5; Week 4: 5; Week 5: 5; Week 6: 5; Week 7: 5
Developer | India | 192 | Week 1: 5; Week 2: 5; Week 3: 5; Week 4: 5; Week 5: 5; Week 6: 5; Week 7: 5
QA | India | 192
Total Efforts in PDs | 75 |  | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost Estimate (USD) | 15680

## Plan - High Level (hidden)
# | Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
1 | Architecture/Design Document + Sign Off | bar: Week 1 to Week 2
2 | Development | bar: Week 3 to Week 13
3 | Integration Testing | bar: Week 14 to Week 15
4 | Test Case Preparation | bar: Week 14 to Week 15
5 | QA | bar: Week 16 to Week 19
6 | UAT Support (Security + Acceptance Testing) | bar: Week 20 to Week 23
7 | IAT Sign Off + Prod Deployment | bar: Week 24
8 | Warranty & Support | bar: Week 25 to Week 28